## Sheet
Type | Code | Description | Min. duration | Most likely duration | Max. duration | Predecessors | Successors | Early start date | Early completion date | Late start date | Late completion date | Is critical
Gate | Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | -1.954e-14 | -1.954e-14 | TRUE
Task | A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 12.0925 | -1.954e-14 | 12.0925 | TRUE
Task | A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 12.0925 | 18.3246 | 12.5765 | 18.8085 | FALSE
Task | A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 12.0925 | 18.8085 | 12.0925 | 18.8085 | TRUE
Task | A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 12.0925 | 16.4275 | 14.4736 | 18.8085 | FALSE
Task | B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 18.8085 | 21.9076 | 18.8085 | 21.9076 | TRUE
Task | B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 21.9076 | 29.2142 | 23.6013 | 30.9078 | FALSE
Task | B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 21.9076 | 30.9078 | 21.9076 | 30.9078 | TRUE
Task | B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 21.9076 | 28.4283 | 24.3871 | 30.9078 | FALSE
Task | C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 30.9078 | 37.7678 | 30.9078 | 37.7678 | TRUE
Task | C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 37.7678 | 45.1812 | 37.7678 | 45.1812 | TRUE
Task | C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 37.7678 | 40.5223 | 42.4267 | 45.1812 | FALSE
Task | D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 45.1812 | 49.2165 | 45.1812 | 49.2165 | TRUE
Task | D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 49.2165 | 60.9356 | 49.2165 | 60.9356 | TRUE
Task | D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 60.9356 | 78.5921 | 60.9356 | 78.5921 | TRUE
Task | E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 78.5921 | 99.9491 | 78.5921 | 99.9491 | TRUE
Task | E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 99.9491 | 111.9664 | 120.8168 | 132.8341 | FALSE
Task | E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 99.9491 | 132.8341 | 99.9491 | 132.8341 | TRUE
Task | F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 132.8341 | 151.8286 | 132.8341 | 151.8286 | TRUE
Task | F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 151.8286 | 156.7348 | 157.113 | 162.0192 | FALSE
Task | F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 151.8286 | 162.0192 | 151.8286 | 162.0192 | TRUE
Task | F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 151.8286 | 156.4198 | 157.4279 | 162.0192 | FALSE
Task | F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 151.8286 | 155.4482 | 158.3995 | 162.0192 | FALSE
Task | G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 162.0192 | 171.5099 | 162.0192 | 171.5099 | TRUE
Task | G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 171.5099 | 177.3832 | 171.5099 | 177.3832 | TRUE
Task | G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 171.5099 | 177.2205 | 171.6726 | 177.3832 | FALSE
Task | G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 171.5099 | 174.5828 | 174.3103 | 177.3832 | FALSE
Task | G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 171.5099 | 175.5184 | 173.3747 | 177.3832 | FALSE
Task | H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 177.3832 | 185.6496 | 177.3832 | 185.6496 | TRUE
Task | H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 185.6496 | 195.7776 | 185.6496 | 195.7776 | TRUE
Task | H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 185.6496 | 188.4671 | 192.9601 | 195.7776 | FALSE
Task | I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 195.7776 | 209.5035 | 195.7776 | 209.5035 | TRUE
Task | I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 195.7776 | 205.0425 | 200.2385 | 209.5035 | FALSE
Task | I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 195.7776 | 199.8132 | 205.4678 | 209.5035 | FALSE
Task | J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 235.9709 | 249.0473 | 235.9709 | 249.0473 | TRUE
Task | J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 209.5035 | 228.4522 | 217.0222 | 235.9709 | FALSE
Task | J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 209.5035 | 235.9709 | 209.5035 | 235.9709 | TRUE
Task | K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 249.0473 | 268.1621 | 249.0473 | 268.1621 | TRUE
Task | L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 268.1621 | 288.7371 | 273.2251 | 293.8002 | FALSE
Task | L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 268.1621 | 284.3593 | 277.6029 | 293.8002 | FALSE
Task | L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 268.1621 | 275.4442 | 286.518 | 293.8002 | FALSE
Task | L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 268.1621 | 271.5717 | 290.3906 | 293.8002 | FALSE
Task | L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 268.1621 | 273.2972 | 288.665 | 293.8002 | FALSE
Task | L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 268.1621 | 281.332 | 280.6302 | 293.8002 | FALSE
Task | L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 268.1621 | 293.8002 | 268.1621 | 293.8002 | TRUE
Task | M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 293.8002 | 300.2153 | 293.8002 | 300.2153 | TRUE
Task | M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 300.2153 | 311.3519 | 300.2153 | 311.3519 | TRUE
Task | M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 300.2153 | 310.1045 | 301.4627 | 311.3519 | FALSE
Task | M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 300.2153 | 306.3821 | 305.1851 | 311.3519 | FALSE
Task | N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 311.3519 | 318.2909 | 311.3519 | 318.2909 | TRUE
Task | N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 318.2909 | 337.067 | 318.2909 | 337.067 | TRUE
Task | O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 337.067 | 340.1169 | 346.705 | 349.7549 | FALSE
Task | O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 337.067 | 349.7549 | 337.067 | 349.7549 | TRUE
Task | O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 337.067 | 340.9467 | 345.8752 | 349.7549 | FALSE
Task | O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 349.7549 | 353.2826 | 351.6 | 355.1277 | FALSE
Task | O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 349.7549 | 355.1277 | 349.7549 | 355.1277 | TRUE
Task | P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 355.1277 | 359.5109 | 357.644 | 362.0272 | FALSE
Task | P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 355.1277 | 362.0272 | 355.1277 | 362.0272 | TRUE
Task | P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 355.1277 | 359.353 | 357.8019 | 362.0272 | FALSE
Task | Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 362.0272 | 366.3032 | 362.0272 | 366.3032 | TRUE
Task | Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 366.3032 | 370.4195 | 366.3032 | 370.4195 | TRUE
Task | Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 370.4195 | 371.4195 | 370.4195 | 371.4195 | TRUE
Gate | Completion |  | 0 | 0 | 0 | Q.3 |  | 371.4195 | 371.4195 | 371.4195 | 371.4195 | TRUE