## Sheet
Type | Code | Description | Min. duration | Most likely duration | Max. duration | Predecessors | Successors | Early start date | Early completion date | Late start date | Late completion date | Is critical
Gate | Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | 1.4211e-14 | 1.4211e-14 | FALSE
Task | A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 18 | 1.4211e-14 | 13.443 | FALSE
Task | A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 18 | 27 | 15.0819 | 19.5258 | FALSE
Task | A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 18 | 27 | 13.443 | 19.5258 | FALSE
Task | A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 18 | 24 | 15.637 | 19.5258 | FALSE
Task | B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 27 | 33 | 19.5258 | 22.3256 | FALSE
Task | B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 33 | 42 | 25.7981 | 29.4182 | FALSE
Task | B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 33 | 45 | 22.3256 | 29.4182 | FALSE
Task | B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 33 | 42 | 25.0455 | 29.4182 | FALSE
Task | C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 45 | 57 | 29.4182 | 38.7291 | FALSE
Task | C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 57 | 66 | 38.7291 | 43.3814 | FALSE
Task | C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 57 | 63 | 39.1135 | 43.3814 | FALSE
Task | D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 66 | 72 | 43.3814 | 46.9809 | FALSE
Task | D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 72 | 90 | 46.9809 | 55.9728 | FALSE
Task | D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 90 | 120 | 55.9728 | 68.043 | FALSE
Task | E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 120 | 147 | 68.043 | 85.4575 | FALSE
Task | E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 147 | 177 | 97.7232 | 115.7909 | FALSE
Task | E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 147 | 192 | 85.4575 | 115.7909 | FALSE
Task | F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 192 | 216 | 115.7909 | 126.1724 | FALSE
Task | F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 216 | 225 | 129.7779 | 136.1632 | FALSE
Task | F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 216 | 234 | 126.1724 | 136.1632 | FALSE
Task | F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 216 | 225 | 130.5429 | 136.1632 | FALSE
Task | F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 216 | 222 | 132.8333 | 136.1632 | FALSE
Task | G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 234 | 246 | 136.1632 | 142.051 | FALSE
Task | G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 246 | 258 | 142.051 | 147.7975 | FALSE
Task | G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 246 | 255 | 143.5702 | 147.7975 | FALSE
Task | G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 246 | 252 | 143.2288 | 147.7975 | FALSE
Task | G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 246 | 252 | 143.1906 | 147.7975 | FALSE
Task | H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 258 | 270 | 147.7975 | 154.9365 | FALSE
Task | H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 270 | 282 | 154.9365 | 160.1606 | FALSE
Task | H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 270 | 276 | 155.5477 | 160.1606 | FALSE
Task | I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 282 | 300 | 160.1606 | 172.3199 | FALSE
Task | I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 282 | 294 | 163.6395 | 172.3199 | FALSE
Task | I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 282 | 288 | 167.9939 | 172.3199 | FALSE
Task | J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 348 | 375 | 206.6225 | 226.4448 | FALSE
Task | J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 300 | 348 | 172.3199 | 206.6225 | FALSE
Task | J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 300 | 342 | 185.8638 | 206.6225 | FALSE
Task | K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 375 | 402 | 226.4448 | 244.7999 | FALSE
Task | L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 402 | 444 | 244.7999 | 270.7601 | FALSE
Task | L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 402 | 426 | 256.2212 | 270.7601 | FALSE
Task | L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 402 | 414 | 261.5344 | 270.7601 | FALSE
Task | L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 402 | 408 | 266.3181 | 270.7601 | FALSE
Task | L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 402 | 408 | 267.7386 | 270.7601 | FALSE
Task | L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 402 | 426 | 257.8185 | 270.7601 | FALSE
Task | L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 402 | 438 | 256.787 | 270.7601 | FALSE
Task | M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 444 | 453 | 270.7601 | 276.8332 | FALSE
Task | M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 453 | 471 | 276.8332 | 290.5903 | FALSE
Task | M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 453 | 465 | 282.1391 | 290.5903 | FALSE
Task | M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 453 | 462 | 284.1285 | 290.5903 | FALSE
Task | N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 471 | 483 | 290.5903 | 299.0421 | FALSE
Task | N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 483 | 510 | 299.0421 | 315.9741 | FALSE
Task | O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 510 | 516 | 324.5193 | 329.2831 | FALSE
Task | O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 510 | 528 | 315.9741 | 329.2831 | FALSE
Task | O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 510 | 516 | 325.2031 | 329.2831 | FALSE
Task | O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 528 | 534 | 329.5299 | 333.4441 | FALSE
Task | O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 528 | 534 | 329.2831 | 333.4441 | FALSE
Task | P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 534 | 540 | 336.0659 | 340.3465 | FALSE
Task | P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 534 | 543 | 333.4441 | 340.3465 | FALSE
Task | P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 534 | 540 | 336.8594 | 340.3465 | FALSE
Task | Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 543 | 549 | 340.3465 | 345.0811 | FALSE
Task | Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 549 | 555 | 345.0811 | 349.2398 | FALSE
Task | Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 555 | 556 | 349.2398 | 350.2398 | FALSE
Gate | Completion |  | 0 | 0 | 0 | Q.3 |  | 556 | 556 | 350.2398 | 350.2398 | FALSE