## Sheet
Type | Code | Description | Min. duration | Most likely duration | Max. duration | Predecessors | Successors | Early start date | Early completion date | Late start date | Late completion date | Is critical
Gate | Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | 0 | 0 | TRUE
Task | A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 12 | 0 | 12 | TRUE
Task | A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 12 | 18 | 12 | 18 | TRUE
Task | A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 12 | 18 | 12 | 18 | TRUE
Task | A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 12 | 16 | 14 | 18 | FALSE
Task | B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 18 | 22 | 18 | 22 | TRUE
Task | B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 22 | 28 | 24 | 30 | FALSE
Task | B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 22 | 30 | 22 | 30 | TRUE
Task | B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 22 | 28 | 24 | 30 | FALSE
Task | C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 30 | 38 | 30 | 38 | TRUE
Task | C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 38 | 44 | 38 | 44 | TRUE
Task | C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 38 | 42 | 40 | 44 | FALSE
Task | D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 44 | 48 | 44 | 48 | TRUE
Task | D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 48 | 60 | 48 | 60 | TRUE
Task | D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 60 | 80 | 60 | 80 | TRUE
Task | E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 80 | 98 | 80 | 98 | TRUE
Task | E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 98 | 118 | 108 | 128 | FALSE
Task | E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 98 | 128 | 98 | 128 | TRUE
Task | F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 128 | 144 | 128 | 144 | TRUE
Task | F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 144 | 150 | 150 | 156 | FALSE
Task | F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 144 | 156 | 144 | 156 | TRUE
Task | F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 144 | 150 | 150 | 156 | FALSE
Task | F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 144 | 148 | 152 | 156 | FALSE
Task | G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 156 | 164 | 156 | 164 | TRUE
Task | G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 164 | 172 | 164 | 172 | TRUE
Task | G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 164 | 170 | 166 | 172 | FALSE
Task | G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 164 | 168 | 168 | 172 | FALSE
Task | G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 164 | 168 | 168 | 172 | FALSE
Task | H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 172 | 180 | 172 | 180 | TRUE
Task | H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 180 | 188 | 180 | 188 | TRUE
Task | H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 180 | 184 | 184 | 188 | FALSE
Task | I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 188 | 200 | 188 | 200 | TRUE
Task | I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 188 | 196 | 192 | 200 | FALSE
Task | I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 188 | 192 | 196 | 200 | FALSE
Task | J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 232 | 250 | 232 | 250 | TRUE
Task | J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 200 | 232 | 200 | 232 | TRUE
Task | J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 200 | 228 | 204 | 232 | FALSE
Task | K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 250 | 268 | 250 | 268 | TRUE
Task | L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 268 | 296 | 268 | 296 | TRUE
Task | L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 268 | 284 | 280 | 296 | FALSE
Task | L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 268 | 276 | 288 | 296 | FALSE
Task | L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 268 | 272 | 292 | 296 | FALSE
Task | L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 268 | 272 | 292 | 296 | FALSE
Task | L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 268 | 284 | 280 | 296 | FALSE
Task | L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 268 | 292 | 272 | 296 | FALSE
Task | M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 296 | 302 | 296 | 302 | TRUE
Task | M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 302 | 314 | 302 | 314 | TRUE
Task | M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 302 | 310 | 306 | 314 | FALSE
Task | M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 302 | 308 | 308 | 314 | FALSE
Task | N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 314 | 322 | 314 | 322 | TRUE
Task | N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 322 | 340 | 322 | 340 | TRUE
Task | O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 340 | 344 | 348 | 352 | FALSE
Task | O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 340 | 352 | 340 | 352 | TRUE
Task | O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 340 | 344 | 348 | 352 | FALSE
Task | O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 352 | 356 | 352 | 356 | TRUE
Task | O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 352 | 356 | 352 | 356 | TRUE
Task | P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 356 | 360 | 358 | 362 | FALSE
Task | P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 356 | 362 | 356 | 362 | TRUE
Task | P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 356 | 360 | 358 | 362 | FALSE
Task | Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 362 | 366 | 362 | 366 | TRUE
Task | Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 366 | 370 | 366 | 370 | TRUE
Task | Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 370 | 371 | 370 | 371 | TRUE
Gate | Completion |  | 0 | 0 | 0 | Q.3 |  | 371 | 371 | 371 | 371 | TRUE