## Sheet
Type | Code | Description | Min. duration | Most likely duration | Max. duration | Predecessors | Successors | Early start date | Early completion date | Late start date | Late completion date | Is critical
Gate | Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | 4.4409e-14 | 4.4409e-14 | FALSE
Task | A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 12.8241 | 4.4409e-14 | 12.8241 | FALSE
Task | A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 12.8241 | 19.842 | 12.8241 | 19.842 | FALSE
Task | A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 12.8241 | 18.6809 | 13.9852 | 19.842 | FALSE
Task | A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 12.8241 | 16.1042 | 16.5619 | 19.842 | FALSE
Task | B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 19.842 | 23.8621 | 19.842 | 23.8621 | FALSE
Task | B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 23.8621 | 28.2902 | 28.8166 | 33.2448 | FALSE
Task | B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 23.8621 | 33.2448 | 23.8621 | 33.2448 | FALSE
Task | B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 23.8621 | 30.8694 | 26.2374 | 33.2448 | FALSE
Task | C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 33.2448 | 41.9949 | 33.2448 | 41.9949 | FALSE
Task | C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 41.9949 | 47.5261 | 41.9949 | 47.5261 | FALSE
Task | C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 41.9949 | 46.3611 | 43.1598 | 47.5261 | FALSE
Task | D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 47.5261 | 51.827 | 47.5261 | 51.827 | FALSE
Task | D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 51.827 | 66.0369 | 51.827 | 66.0369 | FALSE
Task | D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 66.0369 | 89.9106 | 66.0369 | 89.9106 | FALSE
Task | E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 89.9106 | 103.5884 | 89.9106 | 103.5884 | FALSE
Task | E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 103.5884 | 127.0277 | 103.5884 | 127.0277 | FALSE
Task | E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 103.5884 | 126.3055 | 104.3106 | 127.0277 | FALSE
Task | F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 127.0277 | 138.3623 | 127.0277 | 138.3623 | FALSE
Task | F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 138.3623 | 144.5065 | 143.6645 | 149.8087 | FALSE
Task | F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 138.3623 | 149.8087 | 138.3623 | 149.8087 | FALSE
Task | F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 138.3623 | 143.8043 | 144.3667 | 149.8087 | FALSE
Task | F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 138.3623 | 143.1731 | 144.9979 | 149.8087 | FALSE
Task | G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 149.8087 | 155.6244 | 149.8087 | 155.6244 | FALSE
Task | G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 155.6244 | 162.3686 | 155.6244 | 162.3686 | FALSE
Task | G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 155.6244 | 161.786 | 156.2071 | 162.3686 | FALSE
Task | G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 155.6244 | 159.9307 | 158.0624 | 162.3686 | FALSE
Task | G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 155.6244 | 160.391 | 157.6021 | 162.3686 | FALSE
Task | H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 162.3686 | 171.4356 | 162.3686 | 171.4356 | FALSE
Task | H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 171.4356 | 180.7499 | 171.4356 | 180.7499 | FALSE
Task | H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 171.4356 | 175.846 | 176.3395 | 180.7499 | FALSE
Task | I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 180.7499 | 192.1478 | 180.7499 | 192.1478 | FALSE
Task | I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 180.7499 | 189.2052 | 183.6925 | 192.1478 | FALSE
Task | I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 180.7499 | 185.5136 | 187.3841 | 192.1478 | FALSE
Task | J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 228.8551 | 243.4515 | 228.8551 | 243.4515 | FALSE
Task | J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 192.1478 | 228.8551 | 192.1478 | 228.8551 | FALSE
Task | J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 192.1478 | 220.4523 | 200.5507 | 228.8551 | FALSE
Task | K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 243.4515 | 264.7004 | 243.4515 | 264.7004 | TRUE
Task | L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 264.7004 | 290.3144 | 264.7004 | 290.3144 | TRUE
Task | L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 264.7004 | 280.706 | 274.3088 | 290.3144 | FALSE
Task | L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 264.7004 | 272.8739 | 282.1409 | 290.3144 | FALSE
Task | L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 264.7004 | 268.9096 | 286.1053 | 290.3144 | FALSE
Task | L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 264.7004 | 268.1741 | 286.8408 | 290.3144 | FALSE
Task | L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 264.7004 | 282.0679 | 272.9469 | 290.3144 | FALSE
Task | L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 264.7004 | 286.6332 | 268.3816 | 290.3144 | FALSE
Task | M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 290.3144 | 294.9851 | 290.3144 | 294.9851 | TRUE
Task | M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 294.9851 | 306.0306 | 294.9851 | 306.0306 | TRUE
Task | M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 294.9851 | 303.3347 | 297.681 | 306.0306 | FALSE
Task | M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 294.9851 | 302.0891 | 298.9266 | 306.0306 | FALSE
Task | N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 306.0306 | 312.5289 | 306.0306 | 312.5289 | TRUE
Task | N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 312.5289 | 328.2473 | 312.5289 | 328.2473 | TRUE
Task | O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 328.2473 | 332.8794 | 331.9554 | 336.5875 | FALSE
Task | O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 328.2473 | 336.5875 | 328.2473 | 336.5875 | TRUE
Task | O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 328.2473 | 332.1083 | 332.7265 | 336.5875 | FALSE
Task | O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 336.5875 | 339.7333 | 337.995 | 341.1408 | FALSE
Task | O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 336.5875 | 341.1408 | 336.5875 | 341.1408 | TRUE
Task | P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 341.1408 | 344.7885 | 342.1063 | 345.7539 | FALSE
Task | P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 341.1408 | 345.7539 | 341.1408 | 345.7539 | TRUE
Task | P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 341.1408 | 344.8768 | 342.0179 | 345.7539 | FALSE
Task | Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 345.7539 | 349.321 | 345.7539 | 349.321 | TRUE
Task | Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 349.321 | 353.1484 | 349.321 | 353.1484 | TRUE
Task | Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 353.1484 | 354.1484 | 353.1484 | 354.1484 | TRUE
Gate | Completion |  | 0 | 0 | 0 | Q.3 |  | 354.1484 | 354.1484 | 354.1484 | 354.1484 | TRUE