## Sheet
Type | Code | Description | Min. duration | Most likely duration | Max. duration | Predecessors | Successors | Early start date | Early completion date | Late start date | Late completion date | Is critical
Gate | Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | -1.954e-14 | -1.954e-14 | FALSE
Task | A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 11.593 | -1.954e-14 | 11.593 | FALSE
Task | A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 11.593 | 18.1426 | 11.593 | 18.1426 | FALSE
Task | A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 11.593 | 15.2709 | 14.4647 | 18.1426 | FALSE
Task | A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 11.593 | 16.1567 | 13.5788 | 18.1426 | FALSE
Task | B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 18.1426 | 22.4922 | 18.1426 | 22.4922 | FALSE
Task | B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 22.4922 | 25.7758 | 25.1054 | 28.3891 | FALSE
Task | B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 22.4922 | 28.3891 | 22.4922 | 28.3891 | FALSE
Task | B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 22.4922 | 27.7897 | 23.0915 | 28.3891 | FALSE
Task | C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 28.3891 | 36.2586 | 28.3891 | 36.2586 | FALSE
Task | C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 36.2586 | 43.2013 | 36.2586 | 43.2013 | FALSE
Task | C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 36.2586 | 41.0794 | 38.3804 | 43.2013 | FALSE
Task | D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 43.2013 | 46.7908 | 43.2013 | 46.7908 | FALSE
Task | D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 46.7908 | 55.1874 | 46.7908 | 55.1874 | FALSE
Task | D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 55.1874 | 73.8971 | 55.1874 | 73.8971 | FALSE
Task | E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 73.8971 | 95.1335 | 73.8971 | 95.1335 | TRUE
Task | E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 95.1335 | 113.1472 | 104.6016 | 122.6154 | FALSE
Task | E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 95.1335 | 122.6154 | 95.1335 | 122.6154 | TRUE
Task | F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 122.6154 | 141.0702 | 122.6154 | 141.0702 | TRUE
Task | F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 141.0702 | 146.7991 | 145.4907 | 151.2195 | FALSE
Task | F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 141.0702 | 151.2195 | 141.0702 | 151.2195 | TRUE
Task | F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 141.0702 | 145.9932 | 146.2965 | 151.2195 | FALSE
Task | F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 141.0702 | 145.3236 | 146.9661 | 151.2195 | FALSE
Task | G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 151.2195 | 158.0883 | 151.2195 | 158.0883 | TRUE
Task | G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 158.0883 | 165.3742 | 158.0883 | 165.3742 | TRUE
Task | G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 158.0883 | 165.2292 | 158.2333 | 165.3742 | FALSE
Task | G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 158.0883 | 160.6432 | 162.8193 | 165.3742 | FALSE
Task | G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 158.0883 | 162.3068 | 161.1556 | 165.3742 | FALSE
Task | H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 165.3742 | 173.788 | 165.3742 | 173.788 | TRUE
Task | H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 173.788 | 183.1876 | 173.788 | 183.1876 | TRUE
Task | H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 173.788 | 177.4886 | 179.487 | 183.1876 | FALSE
Task | I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 183.1876 | 195.9307 | 183.1876 | 195.9307 | TRUE
Task | I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 183.1876 | 192.0642 | 187.0541 | 195.9307 | FALSE
Task | I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 183.1876 | 186.3986 | 192.7197 | 195.9307 | FALSE
Task | J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 233.98 | 244.4595 | 233.98 | 244.4595 | TRUE
Task | J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 195.9307 | 233.98 | 195.9307 | 233.98 | TRUE
Task | J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 195.9307 | 224.0927 | 205.818 | 233.98 | FALSE
Task | K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 244.4595 | 263.6686 | 244.4595 | 263.6686 | TRUE
Task | L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 263.6686 | 293.8594 | 263.6686 | 293.8594 | TRUE
Task | L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 263.6686 | 279.3561 | 278.1719 | 293.8594 | FALSE
Task | L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 263.6686 | 269.3433 | 288.1847 | 293.8594 | FALSE
Task | L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 263.6686 | 267.1301 | 290.3979 | 293.8594 | FALSE
Task | L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 263.6686 | 268.1966 | 289.3314 | 293.8594 | FALSE
Task | L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 263.6686 | 281.7691 | 275.7589 | 293.8594 | FALSE
Task | L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 263.6686 | 281.6015 | 275.9265 | 293.8594 | FALSE
Task | M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 293.8594 | 298.6237 | 293.8594 | 298.6237 | TRUE
Task | M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 298.6237 | 306.617 | 299.8558 | 307.8491 | FALSE
Task | M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 298.6237 | 307.8491 | 298.6237 | 307.8491 | TRUE
Task | M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 298.6237 | 305.27 | 301.2029 | 307.8491 | FALSE
Task | N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 307.8491 | 314.6174 | 307.8491 | 314.6174 | TRUE
Task | N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 314.6174 | 328.6908 | 314.6174 | 328.6908 | TRUE
Task | O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 328.6908 | 331.6575 | 337.026 | 339.9927 | FALSE
Task | O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 328.6908 | 339.9927 | 328.6908 | 339.9927 | TRUE
Task | O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 328.6908 | 332.6806 | 336.0028 | 339.9927 | FALSE
Task | O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 339.9927 | 342.3127 | 340.6619 | 342.9819 | FALSE
Task | O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 339.9927 | 342.9819 | 339.9927 | 342.9819 | TRUE
Task | P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 342.9819 | 347.7325 | 345.2457 | 349.9963 | FALSE
Task | P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 342.9819 | 349.9963 | 342.9819 | 349.9963 | TRUE
Task | P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 342.9819 | 345.3637 | 347.6145 | 349.9963 | FALSE
Task | Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 349.9963 | 353.6918 | 349.9963 | 353.6918 | TRUE
Task | Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 353.6918 | 358.1337 | 353.6918 | 358.1337 | TRUE
Task | Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 358.1337 | 359.1337 | 358.1337 | 359.1337 | TRUE
Gate | Completion |  | 0 | 0 | 0 | Q.3 |  | 359.1337 | 359.1337 | 359.1337 | 359.1337 | TRUE