## Sheet
Type | Code | Description | Min. duration | Most likely duration | Max. duration | Predecessors | Successors | Early start date | Early completion date | Late start date | Late completion date | Is critical
Gate | Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | -2.6645e-14 | -2.6645e-14 | TRUE
Task | A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 11.7608 | -2.6645e-14 | 11.7608 | TRUE
Task | A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 11.7608 | 15.3064 | 13.4753 | 17.0209 | FALSE
Task | A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 11.7608 | 17.0209 | 11.7608 | 17.0209 | TRUE
Task | A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 11.7608 | 15.6182 | 13.1635 | 17.0209 | FALSE
Task | B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 17.0209 | 21.1349 | 17.0209 | 21.1349 | TRUE
Task | B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 21.1349 | 26.8196 | 21.315 | 26.9997 | FALSE
Task | B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 21.1349 | 26.9997 | 21.1349 | 26.9997 | TRUE
Task | B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 21.1349 | 26.491 | 21.6437 | 26.9997 | FALSE
Task | C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 26.9997 | 36.9791 | 26.9997 | 36.9791 | TRUE
Task | C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 36.9791 | 41.7437 | 36.9791 | 41.7437 | TRUE
Task | C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 36.9791 | 39.9818 | 38.741 | 41.7437 | FALSE
Task | D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 41.7437 | 44.8824 | 41.7437 | 44.8824 | TRUE
Task | D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 44.8824 | 59.0499 | 44.8824 | 59.0499 | TRUE
Task | D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 59.0499 | 79.663 | 59.0499 | 79.663 | TRUE
Task | E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 79.663 | 95.8303 | 79.663 | 95.8303 | TRUE
Task | E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 95.8303 | 112.1925 | 116.3445 | 132.7067 | FALSE
Task | E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 95.8303 | 132.7067 | 95.8303 | 132.7067 | TRUE
Task | F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 132.7067 | 145 | 132.7067 | 145 | TRUE
Task | F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 145 | 149.3933 | 157.7021 | 162.0954 | FALSE
Task | F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 145 | 162.0954 | 145 | 162.0954 | TRUE
Task | F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 145 | 150.8194 | 156.276 | 162.0954 | FALSE
Task | F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 145 | 149.2914 | 157.804 | 162.0954 | FALSE
Task | G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 162.0954 | 169.9021 | 162.0954 | 169.9021 | TRUE
Task | G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 169.9021 | 178.22 | 169.9021 | 178.22 | TRUE
Task | G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 169.9021 | 177.8253 | 170.2968 | 178.22 | FALSE
Task | G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 169.9021 | 173.6839 | 174.4382 | 178.22 | FALSE
Task | G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 169.9021 | 173.3742 | 174.7479 | 178.22 | FALSE
Task | H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 178.22 | 186.9754 | 178.22 | 186.9754 | TRUE
Task | H.2 | Roof Installation | 4 | 8 | 12 | H.1 |  | 186.9754 | 194.5227 | 186.9754 | 194.5227 | TRUE
Task | H.3 | Roof Isolation | 2 | 4 | 6 | H.1 |  | 186.9754 | 189.8691 | 186.9754 | 189.8691 | TRUE
Gate | Test_Gate | Test gate | 0 | 0 | 0 | H.2, H.3 | I.1, I.2, I.3 | 194.5227 | 194.5227 | 194.5227 | 194.5227 | TRUE
Task | I.1 | Installation of Electric | 6 | 12 | 18 | Test_Gate | J.2, J.3 | 194.5227 | 210.7211 | 194.5227 | 210.7211 | TRUE
Task | I.2 | Installation of Plumbing | 4 | 8 | 12 | Test_Gate | J.2, J.3 | 194.5227 | 200.6647 | 204.579 | 210.7211 | FALSE
Task | I.3 | Installation of Fire System | 2 | 4 | 6 | Test_Gate | J.2, J.3 | 194.5227 | 197.5225 | 207.7213 | 210.7211 | FALSE
Task | J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 242.1946 | 258.6817 | 242.1946 | 258.6817 | TRUE
Task | J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 210.7211 | 242.1946 | 210.7211 | 242.1946 | TRUE
Task | J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 210.7211 | 232.1061 | 220.8095 | 242.1946 | FALSE
Task | K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 258.6817 | 275.9636 | 258.6817 | 275.9636 | TRUE
Task | L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 275.9636 | 302.8416 | 275.9636 | 302.8416 | TRUE
Task | L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 275.9636 | 294.6278 | 284.1773 | 302.8416 | FALSE
Task | L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 275.9636 | 283.8613 | 294.9439 | 302.8416 | FALSE
Task | L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 275.9636 | 280.4076 | 298.3976 | 302.8416 | FALSE
Task | L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 275.9636 | 279.7202 | 299.0849 | 302.8416 | FALSE
Task | L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 275.9636 | 292.9675 | 285.8376 | 302.8416 | FALSE
Task | L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 275.9636 | 295.365 | 283.4401 | 302.8416 | FALSE
Task | M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 302.8416 | 306.8243 | 302.8416 | 306.8243 | TRUE
Task | M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 306.8243 | 316.0248 | 306.8243 | 316.0248 | TRUE
Task | M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 306.8243 | 314.4138 | 308.4353 | 316.0248 | FALSE
Task | M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 306.8243 | 313.8535 | 308.9956 | 316.0248 | FALSE
Task | N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 316.0248 | 324.0874 | 316.0248 | 324.0874 | TRUE
Task | N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 324.0874 | 346.4151 | 324.0874 | 346.4151 | TRUE
Task | O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 346.4151 | 352.3085 | 347.4574 | 353.3508 | FALSE
Task | O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 346.4151 | 353.3508 | 346.4151 | 353.3508 | TRUE
Task | O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 346.4151 | 348.8501 | 350.9157 | 353.3508 | FALSE
Task | O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 353.3508 | 357.8587 | 353.3508 | 357.8587 | TRUE
Task | O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 353.3508 | 357.7875 | 353.4219 | 357.8587 | FALSE
Task | P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 357.8587 | 361.6833 | 361.1282 | 364.9529 | FALSE
Task | P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 357.8587 | 364.9529 | 357.8587 | 364.9529 | TRUE
Task | P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 357.8587 | 360.8013 | 362.0102 | 364.9529 | FALSE
Task | Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 364.9529 | 368.3801 | 364.9529 | 368.3801 | TRUE
Task | Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 368.3801 | 372.847 | 368.3801 | 372.847 | TRUE
Task | Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 372.847 | 373.847 | 372.847 | 373.847 | TRUE
Gate | Completion |  | 0 | 0 | 0 | Q.3 |  | 373.847 | 373.847 | 373.847 | 373.847 | TRUE