## Sheet
Type | Code | Description | Min. duration | Most likely duration | Max. duration | Predecessors | Successors | Early start date | Early completion date | Late start date | Late completion date | Is critical
Gate | Start |  | 0 | 0 | 0 |  | A.1 | 0 | 0 | 4.6185e-14 | 4.6185e-14 | TRUE
Task | A.1 | Building Design | 6 | 12 | 18 | Start | A.2, A.3, A.4 | 0 | 7.7448 | 4.6185e-14 | 7.7448 | TRUE
Task | A.2 | Electrical Design | 3 | 6 | 9 | A.1 | B.1 | 7.7448 | 13.7392 | 10.3303 | 16.3247 | FALSE
Task | A.3 | Plumbing Design | 3 | 6 | 9 | A.1 | B.1 | 7.7448 | 16.3247 | 7.7448 | 16.3247 | TRUE
Task | A.4 | Fire System Design | 2 | 4 | 6 | A.1 | B.1 | 7.7448 | 11.1116 | 12.9578 | 16.3247 | FALSE
Task | B.1 | Signing Project Contract | 2 | 4 | 6 | A.2, A.3, A.4 | B.2, B.3, B.4 | 16.3247 | 20.2102 | 16.3247 | 20.2102 | TRUE
Task | B.2 | Project Permit | 3 | 6 | 9 | B.1 | C.1 | 20.2102 | 25.2541 | 24.0761 | 29.12 | FALSE
Task | B.3 | Electrical Permit | 4 | 8 | 12 | B.1 | C.1 | 20.2102 | 29.12 | 20.2102 | 29.12 | TRUE
Task | B.4 | Plumbing Permit | 3 | 6 | 9 | B.1 | C.1 | 20.2102 | 25.1245 | 24.2058 | 29.12 | FALSE
Task | C.1 | Installation of Mobilization Building | 4 | 8 | 12 | B.2, B.3, B.4 | C.2, C.3 | 29.12 | 40.6338 | 29.12 | 40.6338 | TRUE
Task | C.2 | Road Work | 3 | 6 | 9 | C.1 | D.1 | 40.6338 | 46.478 | 40.6338 | 46.478 | TRUE
Task | C.3 | Fence Work | 2 | 4 | 6 | C.1 | D.1 | 40.6338 | 45.5393 | 41.5726 | 46.478 | FALSE
Task | D.1 | Clearing and Grubbing | 2 | 4 | 6 | C.2, C.3 | D.2 | 46.478 | 49.7033 | 46.478 | 49.7033 | TRUE
Task | D.2 | Excavation | 6 | 12 | 18 | D.1 | D.3 | 49.7033 | 61.4446 | 49.7033 | 61.4446 | TRUE
Task | D.3 | Filling | 10 | 20 | 30 | D.2 | E.1 | 61.4446 | 79.7124 | 61.4446 | 79.7124 | TRUE
Task | E.1 | Pile | 9 | 18 | 27 | D.3 | E.2, E.3 | 79.7124 | 101.5239 | 79.7124 | 101.5239 | TRUE
Task | E.2 | Concrete | 10 | 20 | 30 | E.1 | F.1 | 101.5239 | 116.8795 | 124.1433 | 139.4989 | FALSE
Task | E.3 | Raft Foundation | 15 | 30 | 45 | E.1 | F.1 | 101.5239 | 139.4989 | 101.5239 | 139.4989 | TRUE
Task | F.1 | Column and Curtain Wall | 8 | 16 | 24 | E.2, E.3 | F.2, F.3, F.4, F.5 | 139.4989 | 153.8656 | 139.4989 | 153.8656 | TRUE
Task | F.2 | Slab | 3 | 6 | 9 | F.1 | G.1 | 153.8656 | 160.8368 | 161.627 | 168.5982 | FALSE
Task | F.3 | Slab Insulation | 6 | 12 | 18 | F.1 | G.1 | 153.8656 | 168.5982 | 153.8656 | 168.5982 | TRUE
Task | F.4 | Masonry | 3 | 6 | 9 | F.1 | G.1 | 153.8656 | 159.0611 | 163.4027 | 168.5982 | FALSE
Task | F.5 | Upper Slab | 2 | 4 | 6 | F.1 | G.1 | 153.8656 | 157.3329 | 165.1309 | 168.5982 | FALSE
Task | G.1 | Column and Curtain Wall | 4 | 8 | 12 | F.2, F.3, F.4, F.5 | G.2, G.3, G.4, G.5 | 168.5982 | 176.7629 | 168.5982 | 176.7629 | TRUE
Task | G.2 | Slab | 4 | 8 | 12 | G.1 | H.1 | 176.7629 | 184.1574 | 176.7629 | 184.1574 | TRUE
Task | G.3 | Slab Insulation | 3 | 6 | 9 | G.1 | H.1 | 176.7629 | 180.6631 | 180.2572 | 184.1574 | FALSE
Task | G.4 | Masonry | 2 | 4 | 6 | G.1 | H.1 | 176.7629 | 181.7743 | 179.146 | 184.1574 | FALSE
Task | G.5 | Upper Slab | 2 | 4 | 6 | G.1 | H.1 | 176.7629 | 179.8702 | 181.0502 | 184.1574 | FALSE
Task | H.1 | Roof Beam Installation | 4 | 8 | 12 | G.2, G.3, G.4, G.5 | H.2, H.3 | 184.1574 | 193.9173 | 184.1574 | 193.9173 | TRUE
Task | H.2 | Roof Installation | 4 | 8 | 12 | H.1 | I.1, I.2, I.3 | 193.9173 | 199.0183 | 193.9173 | 199.0183 | TRUE
Task | H.3 | Roof Isolation | 2 | 4 | 6 | H.1 | I.1, I.2, I.3 | 193.9173 | 197.6723 | 195.2633 | 199.0183 | FALSE
Task | I.1 | Installation of Electric | 6 | 12 | 18 | H.2, H.3 | J.2, J.3 | 199.0183 | 209.9369 | 199.0183 | 209.9369 | TRUE
Task | I.2 | Installation of Plumbing | 4 | 8 | 12 | H.2, H.3 | J.2, J.3 | 199.0183 | 209.9195 | 199.0358 | 209.9369 | FALSE
Task | I.3 | Installation of Fire System | 2 | 4 | 6 | H.2, H.3 | J.2, J.3 | 199.0183 | 202.9125 | 206.0427 | 209.9369 | FALSE
Task | J.1 | Drywall | 9 | 18 | 27 | J.2, J.3 | K.1 | 242.9275 | 260.7555 | 242.9275 | 260.7555 | TRUE
Task | J.2 | Interior Brick Wall | 16 | 32 | 48 | I.1, I.2, I.3 | J.1 | 209.9369 | 236.2985 | 216.5659 | 242.9275 | FALSE
Task | J.3 | Exterior Brick Wall | 14 | 28 | 42 | I.1, I.2, I.3 | J.1 | 209.9369 | 242.9275 | 209.9369 | 242.9275 | TRUE
Task | K.1 | Plaster (ext-int) | 9 | 18 | 27 | J.1 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | 260.7555 | 272.5243 | 260.7555 | 272.5243 | TRUE
Task | L.1 | Travertine Coating | 14 | 28 | 42 | K.1 | M.1 | 272.5243 | 301.4157 | 272.5243 | 301.4157 | TRUE
Task | L.2 | Marble Coating | 8 | 16 | 24 | K.1 | M.1 | 272.5243 | 286.0235 | 287.9164 | 301.4157 | FALSE
Task | L.3 | Tile Mosaic Coating | 4 | 8 | 12 | K.1 | M.1 | 272.5243 | 281.2536 | 292.6863 | 301.4157 | FALSE
Task | L.4 | Ceramic Coating | 2 | 4 | 6 | K.1 | M.1 | 272.5243 | 276.2367 | 297.7033 | 301.4157 | FALSE
Task | L.5 | Epoxy | 2 | 4 | 6 | K.1 | M.1 | 272.5243 | 275.3539 | 298.5861 | 301.4157 | FALSE
Task | L.6 | Suspended Ceiling Cover | 8 | 16 | 24 | K.1 | M.1 | 272.5243 | 287.9868 | 285.9532 | 301.4157 | FALSE
Task | L.7 | Outer Wall Covering | 12 | 24 | 36 | K.1 | M.1 | 272.5243 | 292.0469 | 281.893 | 301.4157 | FALSE
Task | M.1 | Fenestration Installation | 3 | 6 | 9 | L.1, L.2, L.3, L.4, L.5, L.6, L.7 | M.2, M.3, M.4 | 301.4157 | 305.4143 | 301.4157 | 305.4143 | TRUE
Task | M.2 | Wood Work | 6 | 12 | 18 | M.1 | N.1 | 305.4143 | 313.1276 | 305.4143 | 313.1276 | TRUE
Task | M.3 | Aluminium Joinery | 4 | 8 | 12 | M.1 | N.1 | 305.4143 | 313.0257 | 305.5162 | 313.1276 | FALSE
Task | M.4 | Metal Joinery | 3 | 6 | 9 | M.1 | N.1 | 305.4143 | 311.5218 | 307.0201 | 313.1276 | FALSE
Task | N.1 | Interior Paint | 4 | 8 | 12 | M.2, M.3, M.4 | N.2 | 313.1276 | 322.5107 | 313.1276 | 322.5107 | TRUE
Task | N.2 | Exterior Paint | 9 | 18 | 27 | N.1 | O.1, O.2, O.3 | 322.5107 | 338.6899 | 322.5107 | 338.6899 | TRUE
Task | O.1 | Ventilation System | 2 | 4 | 6 | N.2 | O.4, O.5 | 338.6899 | 341.9032 | 351.5369 | 354.7502 | FALSE
Task | O.2 | Clean-Waste Water | 6 | 12 | 18 | N.2 | O.4, O.5 | 338.6899 | 354.7502 | 338.6899 | 354.7502 | TRUE
Task | O.3 | Rain Water | 2 | 4 | 6 | N.2 | O.4, O.5 | 338.6899 | 344.3624 | 349.0777 | 354.7502 | FALSE
Task | O.4 | Mechanical Automation | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 354.7502 | 359.1181 | 354.7502 | 359.1181 | TRUE
Task | O.5 | Mechanical Electric Work | 2 | 4 | 6 | O.1, O.2, O.3 | P.1, P.2, P.3 | 354.7502 | 358.8169 | 355.0514 | 359.1181 | FALSE
Task | P.1 | Fire Protection System | 2 | 4 | 6 | O.4, O.5 | Q.1 | 359.1181 | 362.6336 | 364.0053 | 367.5208 | FALSE
Task | P.2 | Fire Detection System | 3 | 6 | 9 | O.4, O.5 | Q.1 | 359.1181 | 367.5208 | 359.1181 | 367.5208 | TRUE
Task | P.3 | Security Lighting | 2 | 4 | 6 | O.4, O.5 | Q.1 | 359.1181 | 363.848 | 362.7909 | 367.5208 | FALSE
Task | Q.1 | Cleaning | 2 | 4 | 6 | P.1, P.2, P.3 | Q.2 | 367.5208 | 370.8444 | 367.5208 | 370.8444 | TRUE
Task | Q.2 | Final Control | 2 | 4 | 6 | Q.1 | Q.3 | 370.8444 | 375.3933 | 370.8444 | 375.3933 | TRUE
Task | Q.3 | Delivery | 1 | 1 | 1 | Q.2 | Completion | 375.3933 | 376.3933 | 375.3933 | 376.3933 | TRUE
Gate | Completion |  | 0 | 0 | 0 | Q.3 |  | 376.3933 | 376.3933 | 376.3933 | 376.3933 | TRUE